## Dashboard
Dashboard
Queries |  |  | Stories in Sprint
Sprint Query | labels in (selected) |  |  |  | Story Points |  |  |  | Time Spent in each state during sprint
Backlog Query | "Epic Link" = HMIP-2259 and status in ("In Progress","Open") |  | Key | Summary | Start | End | Removed | Status | Open | In Progress | Reopened | Blocked | Resolved | Closed
Analyst Query | "External ID" is not empty and status in ("Resolved") |  | HMIP-2272 | new task | 0 | 0 |  | Open | 3d 19h 12m
Sprint Details |  |  | HMIP-2271 | CLONE - TASK1 | 0 | 8 |  | In Progress | 8h 11m | 3d 19h 45m
Name | hmip Sprint 2 |  | HMIP-1616 | Third Display enablement | 0 | 0 |  | Open | 4d 21h 3m
Status | ACTIVE |  | HMIP-1010 | Opengl with qemu QFont issue | 0 | 2 |  | Blocked | 1d 2h 43m | 8m |  | 3d 18h 11m
Start | 2022-05-13 06:05 |  | HMIP-1640 | Invoice Verification - Neusoft B Samples | 3 | 4 | yes | In Progress | 1 m | 4d 21h 3m | 1 m |  | 1 m
End | 2022-06-01 06:06
Team
User | Name | Email
mahmad | Ahmad, Mumtaz | Mumtaz_Ahmad@mentor.com
unassigned | unassigned | unassigned

## Backlog
Backlog Items
Story | Key | Summary | Status | Reporter | Assignee | Analyst
Story 1 | HMIP-2273 | new task | Open | Ahmad, Mumtaz | Ahmad, Mumtaz | Mumtaz