## Dashboard
Dashboard
Query |  |  | Stories in Sprint
Sprint = 2867 |  |  |  |  | Story Points |  |  | Time Spent in each state during sprint
|  |  | Key | Summary | Start | End | Status | Open | In Progress | Reopened | Blocked | Resolved | Closed
Sprint Details |  |  | HMIP-2272 | new task | 0 | 0 | Open | 3d 5h 12m
Name | hmip Sprint 2 |  | HMIP-2271 | CLONE - TASK1 | 0 | 8 | In Progress | 8h 11m | 3d 5h 44m
Status | ACTIVE |  | HMIP-1640 | Invoice Verification - Neusoft B Samples | 3 | 3 | In Progress | 1 m | 4d 7h 2m | 1 m |  | 1 m
Start | 2022-05-13 06:05 |  | HMIP-1616 | Third Display enablement | 0 | 0 | Open | 4d 7h 2m
End | 2022-06-01 06:06 |  | HMIP-1010 | Opengl with qemu QFont issue | 0 | 2 | Blocked | 1d 2h 43m | 8m |  | 3d 4h 10m
Team
User | Name | Email
mahmad | Ahmad, Mumtaz | Mumtaz_Ahmad@mentor.com
unassigned | unassigned | unassigned